## Slide 1
GÉANT Twinning Programme
Collaborative Capacity Building
between NREN Nepal & CSC/FUNET
Activities and Progress · TNC26, Helsinki, Finland
Rajan Parajuli and Harri Kussisto · Tuesday, 09 June 2026 · Helsinki, Finland

## Slide 2
About the Twinning NRENs
🇳🇵 NREN Nepal
40+ member institutions
Universities, medical schools & research centers
Connected to Asi@Connect & global R&E networks
Key Services
R&E network Connection
eduroam
FileSender
Zoom Meeting
Moodle based LMS Implementation Support
Technical Training
Campus Network Design Advisory
🇫🇮 CSC/FUNET Finland
About 80 member institutions
Universities and Research Insitutions
Connected with GÉANT and NORDUnet
Key Services
R&E network Connection
Supercomputing access
HAKA identity federation
Research support services
eduroam
FileSender
Cloud services
Security services, and etc.
GÉANT Twinning · TNC26 · Helsinki · 09 June 2026

## Slide 3
Twinning Programme Overview
Overall Objective
Forge collaboration by leveraging the respective strengths and experiences of both NRENs in NREN operation, R&E application and services handling, and supporting research communities.
01
eduroam Service Enhancement
eduroam policies development for providers
eduroam CAT deployment and uses of geteduroam application
eduroam user dashboard deployment
eduroam Visitor Access (eVA) deployment
eduroam troubleshooting guide
02
Weekly Meetings & Exchange Visits
Mutual learning and sharing through weekly online meeting and reciprocal in-person exchange visits
03
Supporting REN awareness
Sharing existing awareness materials of both NREN
Revisit existing sensitization materials and also develop new materials
Organize a few meeting with relevant government bodies and share FUNET supports to R&E communities in Finland
GÉANT Twinning · TNC26 · Helsinki · 09 June 2026

## Slide 4
Timeline of the Activities Accomplished
19 Feb 2026
Project
Kick-off
eduroam CAT deployment and get eduroam awareness
Mar 2026
Apr 2026
Eduroam policy development for eduroam providers
Eduroam dashboard development
Mid-Term Review
May 2026
3–5 Jun 2026
NREN Visit
Helsinki
TNC26
Presentation
9 Jun 2026
7
Weekly Knowledge exchange meetings
Completed, expecting a total of 15 meetings
1
Mid-term review
held
3
Focus areas
in progress
26 September
Programme
end date
GÉANT Twinning · TNC26 · Helsinki · 09 June 2026

## Slide 5
Key Progress Achieved
✅ Done
✓
All member institutions enabled for eduroam CAT
✅ Done
✓
geteduroam application support available to all institutions
✅ Done
✓
eduroam dashboards developed for member institutions
✅ Done
✓
eduroam policy developed for eduroam providers
🔄 In Progress
→
Local eVA deployment initiated with support from FUNET and SURF
🔄 In Progress
→
eduroam troubleshooting guide for identification of eduroam connection issues
GÉANT Twinning · TNC26 · Helsinki · 09 June 2026
Revisit existing sensitization materials and also develop new materials
→
🔄 In Progress

## Slide 6
Knowledge Exchange through Weekly Online Meetings
Every Thursday
Topics covered in weekly meetings and during the visit at CSC/FUNET
Policy Framework
Participation policies & agreements
eduroam Dashboard
Analytics & outage detection
R&E Services & Applications
Research & education network services
eVA Deployment
Visitor access with SURF & FUNET
eduroam in Finland
How CSC/FUNET operates nationally
Troubleshooting Guide
eduroam issue resolution
eduroam CAT & geteduroam
Configuration & awareness
REN Awareness Practices
Services portfolio & materials
GÉANT Twinning · TNC26 · Helsinki · 09 June 2026

## Slide 7
NREN Visit to CSC/FUNET — Helsinki
Knowledge Exchange Visit · 3–5 June 2026
Topics Discussed
NREN operations & governance
eduroam services enhancement, hands on demonstration of eVA, CAT deployment, etc.
REN Awareness materials
Research support services
Future collaboration opportunities
Visit Highlights
eduroam technical deep-dive discussions and demonstration
CSC facility tours & service demos
GÉANT Twinning · TNC26 · Helsinki · 09 June 2026
Liaising for possible collaboration among member institutions of both NRENs

## Slide 9
Next Steps & Looking Ahead
Remaining programme milestones through September 2026
Jun–Jul 2026
🔗 Complete eVA Deployment
Finalize eduroam Visitor Access with SURF support
Jun–Jul 2026
📡 eduroam Monitoring
Finalize remote outage detection & monitoring dashboard
Jul 2026
👩‍💻 Administrator Training
Online training for ~20 eduroam administrators across NREN institutions
Jul 2026
📁 Large File Transfer Tests
Demonstrate REN advantages over commercial networks
Aug / Sept 2026
✈️ FUNET Visit to Nepal
Exchange visit including government & stakeholder meetings
Aug 2026
📝 Awareness Materials
Finalize joint presentation & NREN introductory video
Ongoing
🔄 Weekly Collaboration
Continue Thursday meetings; share results via GÉANT & APAN62
September 2026
📋 Final Report
Draft, review & submit final project report to GÉANT
GÉANT Twinning · TNC26 · Helsinki · 09 June 2026

## Slide 10
Key Insights
CSC/FUNET ↔ NREN Nepal
LEARNINGS
THE NREN VALUE PYRAMID
Both NRENs are facing similar challenges — but the severity is different.
Connectivity is the foundation — the ultimate goal is providing R&E services to foster research collaboration and a thriving innovation ecosystem.
Awareness, training, and community engagement matter as much as infrastructure.
Research Ecosystem
Cross-border collaboration & innovation culture
R&E Applications & Services
Connectivity
GÉANT Twinning · TNC26 · Helsinki · 09 June 2026

## Slide 11
Team Members of the Twinning Activities
🇳🇵 NREN Nepal — Team
R
Rajan Parajuli, PhD
Project Lead
I
Indiver Badal
Technical
N
Nirajan Parajuli
Technical
N
Niraj Acharya
Technical
A
Aryan Joshi
Technical
🇫🇮 CSC/FUNET — Team
H
Harri Kuusisto
Project Lead
J
Janne Oksanen
Technical
W
Wenche Backman-Kamila
Technical
Thank you for joining us at TNC26 · Questions welcome
GÉANT Twinning · TNC26 · Helsinki · 09 June 2026